CONSULTANT TO THE DEVELOPMENT OF A MULTIPLE LEARNING PATHWAYS POLICY FRAMEWORK

REQUEST FOR PROPOSAL

(IUL)22-PU/22/2025/323

25th November 2025

MINISTRY OF EDUCATION Republic of Maldives

- INTRODUCTION

The Ministry of Education is seeking consultancy on the development of a multiple learning pathways policy framework.

- SCHEDUE OF CRITICAL DATES

| Action Date | Activity |
| --- | --- |
| 25th November 2025 | Advertised date: |
| 01st December 2025, 2359 hrs. Local Time | Clarification deadline: |
| 03rd December 2025, 1100 hrs. Local Time | Proposal submission deadline: |

- CLARIFICATION

Interested parties may obtain further information on request by writing to the address below.

Procurement Section,

Ministry of Education,

9th Floor, H.Velaanage, 20096

Ameer Ahmed Magu, Male’ City,

Republic of Maldives

Mob: :+( 960) 304 1242 / 304 1249

Email: procurement@moe.gov.mv

CC Email: thaiba@moe.gov.mv

- SUBMISSION REQUIREMENTS

Proposal should contain the following documents and Standard forms in ANNEX A

- Document Checklist (Form 1)

- Technical Proposal Submission Form (Form 2)

- Tenderer Information Sheet (Form 3)

- Description of approach, methodology and work plan for performing the assignment (Form 4)

- Copy of National ID Card

- Curriculum Vitae (CV) of  Team (Form 5)

- Educational Certificates

- Specific experience of contracts of similar nature (Form 6)

- Demonstrations of required experiences listed in this TOR

- Financial Proposal (Form 7)

- PROPOSAL SUBMISSION

| Submission Instruction | Proposal need to be submitted along with required documents mentioned in the request for proposal to: Ministry of Education Ameer Ahmed Magu, Male’, 20079 Republic of Maldives Tel: +( 960) 304 1242 Apply via: http://bit.ly/3JFuFmj |
| --- | --- |
| Submission Deadline | The deadline for the submission of Proposal is: Date: 3rd December 2025, Time: 13:00 hrs. (Local Time) Late submission will not be accepted. |

Terms of Reference

- Background The Ministry of Education (MoE) has initiated an education transformation agenda focused on meeting the diverse needs of all learners. This initiative is supported under the System Transformation Grant in partnership with GPE and UNICEF. Central to this initiative is the development of a comprehensive Multiple Learning Pathways Policy Framework aimed at creating a more inclusive, flexible, and responsive national education system. At present, the existing education structure often limits opportunities for learners who would benefit from alternative or specialized pathways. To address this, there is a pressing need for a policy framework that offers students varied and adaptable educational and career options. This framework must align with students’ individual interests and aspirations, as well as with the evolving demands of the labor market. In response, the MoE seeks the services of a qualified local consultant to design and develop a well-structured Multiple Learning Pathways Policy Framework. The framework should promote inclusivity, relevance, and adaptability within the national education system, and support lifelong learning for all learners.

- Objectives - Develop a comprehensive policy framework for multiple learning pathways, which is aligned with international best practices and national development priorities to provide diverse and flexible opportunities for students to stay in school, learn and transition to work and employment.

- Scope of work - Conduct a literature review on Multiple Learning Pathways including local and international literature. - Conduct stakeholder consultations with educational professionals (MoE technical staff), school principals, teachers, students, young people who have recently completed school, parents, employers, and community representatives to gather in-depth qualitative insights on the effectiveness, strengths, and challenges of existing education pathways, with a special focus on Grades 11 and 12 - Conduct a thorough analysis and assessment of the current education pathways in the Maldives to evaluate their relevance and effectiveness, identify gaps and limitations, and determine areas where improvements or alternative approaches are required. - Conduct a desk review of the existing policy documents and regulations related to multiple learning pathways and develop a concise report that maps current provisions, highlights gaps and contradictions, and a way forward on incorporation of the existing documents into the new Multiple Learning Pathways Policy Framework - Develop a comprehensive Multiple Learning Pathways Policy Framework that outlines clear implementation strategies, practical monitoring and evaluation mechanisms, and actionable recommendations to ensure inclusivity, flexibility, and alignment with both learner needs and labor market demands, explicitly integrating equity dimensions, including gender, disability, and other at-risk or marginalized groups, so that MLP effectively supports the inclusion of all categories of students in line with broader policy goals .

- Deliverables Deliverable; Due by; Estimated cost breakdown (amount in USD). Inception report: Detailed methodology, data collection tools, timeline, and structure of the final report.; 1 week from signing contract; 10%. Desk review report and summary of initial findings.; Within 1 month after submission of the inception report; 20%. Draft report 1: First draft of the Multiple Learning Pathway Framework submitted.; Within 6 weeks after approval of the desk review report; 20%. Validation Workshop: Workshop materials, including PowerPoint presentations and report on the validation workshop.; Within 4 weeks after submission of the draft report 1; 18%. Draft Report 2: Second draft with validation workshop comments.; Within 2 weeks after the validation workshop; 20%. Final Policy Framework: Comprehensive Multiple Learning Pathways Policy Framework that includes implementation strategies, monitoring mechanisms and actionable recommendations. (The M&E framework should include key components such as indicators, data sources, and feedback loops to enable ongoing assessment and continuous improvement. Additionally, the policy framework must explicitly address equity dimensions including gender, disability, and other at-risk or marginalized groups to ensure that MLP supports the inclusion of all learners within the education system); Within 2 weeks after the draft report 2 submission; 12%.

- Travel (if required.) Not required. - Estimated Duration: 04 Months

- Quality assurance Ministry of Education will only make payment based on approval of specific deliverables as listed in this TOR. A technical review committee will be established to oversee the consultancy, quality assure the outputs, and formally sign off on deliverables. This team will be established as follows: a) Three members from Ministry of Education (MoE), including two policy makers and one technical staff b) One member from the National Institute of Education c) One member from UNICEF Maldives The main responsibilities of this team are: - Review draft reports and provide feedback - Validate the final report

- Qualifications or specialized knowledge and/or experience required Academic qualifications: - Master’s degree or higher in education management, education planning, policy or related field of study Knowledge, skills, and experience: - Minimum 5 years of relevant professional experience in education management, education planning, policy analysis, capacity development, curriculum, policy frameworks or sector reform - Demonstrated experience working with government institutions. Previous experience of working with the Ministry of Education will be an added advantage. Competencies: - Strong analytical, research, and report-writing skills, strong facilitation, communication and stakeholder engagement abilities - Ability to deliver high quality outputs within agreed timelines

- Evaluation criteria Evaluation criteria for assessing the qualifications and performance of the consultant. The evaluation procedures will follow that of the Government of Maldives. S. No.; Criteria; Points. TECHICAL EVALUATION; 60. 1; Methodology and approach Description of the methodologies for how the consultant will achieve the terms of reference of the assignment; 20. 2; Client References and Relevant Experience • Minimum 5 years of relevant professional experience in education management, education planning, policy analysis, capacity development, curriculum development, policy frameworks, or sector reform. • Demonstrated experience working with government institutions. Experience with the Ministry of Education will be an added advantage. Each reference should include: – Title of the project – Year and duration – Scope of the project – Outcome of the project – Reference/contact person (optional) - 15 points for a minimum of 5 years of relevant experience (similar scope and size). - 05 points for demonstrated strong analytical, research, and report-writing skills, as well as strong facilitation, communication, and stakeholder-engagement abilities, and the ability to deliver high-quality outputs within agreed timelines.; 20. 3; Educational Qualification - Master’s degree or higher in education management, education planning, policy or related field of study - A Master’s degree in the above or a closely related field will be awarded 20 points.; 20. To pass the technical evaluation, a minimum score of 40 is required. Only candidates who successfully pass the technical evaluation will proceed to the financial evaluation. FINANCIAL EVALUTION. 1; Price (Pro rata basis); 40. TOTAL; 100. A submission must obtain a minimum of 40 out of 60 to pass the technical evaluation. Financial proposals will only be evaluated where the technical proposal has reached the required pass mark. The maximum score of 40 points will be assigned to the financial proposal that provides the lowest overall cost. The financial proposal shall include the facilitation and document preparation cost only..

ANNEX A - FORMS

## FORM 1 – Document Checklist

|  | BID DOCUMENTS | # |
| --- | --- | --- |
|  | Technical Proposal Submission Form (Form 2) | 1 |
|  | Tenderer Information Sheet (Form 3) | 2 |
|  | Description of approach, methodology and work plan for performing the assignment (Form 4) | 3 |
|  | Copy of National ID Card | 4 |
|  | Curriculum Vitae (CV) (Form 5) | 6 |
|  | Educational Certificates | 7 |
|  | Specific experience of contracts of similar nature (Form6) | 8 |
|  | Demonstrations of required experiences listed in this TOR | 9 |
|  | Financial Proposal (Form 7) | 10 |

## FORM 2 – TECHNICAL PROPOSAL SUBMISSION FORM

[Location, Date]

To: [Name and address of Client]

Dear Madam/Sir:

We, the undersigned, offer to provide the “consultant on the development of a multiple learning pathways policy framework” in accordance with your Request for Proposal dated [xxx. I hereby submit our Proposal, which includes all required documents as per Request for Proposal.

We hereby declare that all the information and statements made in this Proposal are true and accept that any misinterpretation contained in it may lead to our disqualification.

If negotiations are held during the period of validity of the Proposal, we undertake to negotiate on the basis of the proposed staff. Our Proposal is binding upon us and subject to the modifications resulting from Contract negotiations.

We undertake, if our Proposal is accepted, to initiate the services and fulfil the terms and conditions related this contract.

We understand you are not bound to accept any Proposal you receive.

Yours sincerely,

Authorized Signature [In full and initials]:

Name and Title of Signatory:

## FORM 3 – TENDERER INFORMATION SHEET

[The Tenderer shall fill in this Form in accordance with the instructions indicated below. No alterations to its format shall be permitted and no substitutions shall be accepted.]

Date:

Announcement No:

| 1. Name |  |
| --- | --- |
| 2. Registration number or ID Card Number |  |
| 3. Address | {insert Tenderer’s legal address in country of registration} |
| 4. Tenderer’s Authorized Representative Information |  |
| Name: |  |
| Address: |  |
| Telephone/Fax numbers: |  |
| Email Address: |  |

## FORM 4: DESCRIPTION OF APPROACH, METHODOLOGY AND WORK PLAN FOR PERFORMING THE ASSIGNMENT

[Technical approach, methodology and work plan are key components of the Technical Proposal. You are suggested to present your Technical Proposal (5-10 pages, inclusive of charts and diagrams) divided into the following two chapters:

- Technical Approach and Methodology,

- Work Plan, and

- Technical Approach and Methodology. In this chapter you should explain your understanding of the objectives of the assignment, approach to the services, methodology for carrying out the activities and obtaining the expected output, and the degree of detail of such output. You should highlight the problems being addressed and their importance, and explain the technical approach you would adopt to address them. You should also explain the methodologies you propose to adopt and highlight the compatibility of those methodologies with the proposed approach.

- Work Plan. In this chapter you should propose the main activities of the assignment, their content and duration, phasing and interrelations, milestones (including interim approvals by the Client), and delivery dates of the reports. The proposed work plan should be consistent with the technical approach and methodology, showing understanding of the TOR and ability to translate them into a feasible working plan.

## FORM 5 – CURRICULUM VITAE (TEAM)

- Name:

- Education [Indicate college/university and other specialized education of staff member, giving names of institutions, degrees obtained, and dates of obtainment]:

- Membership of professional associations

- Other Training

- Countries of work experience [List countries where the consultant has worked in the last ten years]:

- Languages [For each language indicate proficiency: good, fair, or poor in speaking, reading, and writing]:

- Experience/ employment record [Starting with present position, list in reverse order every employment held since graduation, giving for each employment (see format here below): dates of employment, name of employing organization, positions held.]

From [Month/Year] – To [Month/Year]:
Employer:    	
Positions held:

- Summary of projects/assignments undertaken/ role

Name of project/ assignment:

Experience classification: General / specific
Scope of project/ assignment: 
Role/ Position undertaken: 
Period of assignment:

# FORM 6- SPECIFIC EXPERIENCE OF CONTRACTS OF SIMILAR NATURE

List all contracts performed in the last 36 Months

(Reference letters of the completed Projects shall be submitted along with the proposal and this form should be signed and stamped by Tenderer).

| Name of Client | Name of the work | Contract Duration | Contract Signed Date | Contract Completed Date | Contract Value (MVR) |
| --- | --- | --- | --- | --- | --- |

FORM 7 – FINANCIAL PROPOSAL SUBMISSION FORM

[Location, Date]

To:	[Name and address of Client]

Dear Sirs:

We, the undersigned, offer to provide consultant on the development of a multiple learning pathways policy framework in accordance with your Request for Proposal dated [……..] and our Technical Proposal. Our attached Financial Proposal is for the sum of [Insert amount(s) in words and figures1].  This amount is inclusive of the all taxes.

Our Financial Proposal shall be binding upon us subject to the modifications resulting from Contract negotiations, up to expiration of the validity period of the Proposal.

We understand you are not bound to accept any Proposal you receive.

Yours sincerely,

Authorized Signature [In full and initials]:

Name and Title of Signatory:

FINANCIAL PROPOSAL

| SUMMARY OF COSTS |  |  |
| --- | --- | --- |
| # | Description | Amount (in MVR) |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
|  | Subtotal : |  |
|  | All applicable taxes : |  |
|  | Total Amount of Financial Proposal: |  |

Note:

- Bidder is liable to clarify and include all relevant tax for the assignment.